## Revision Block
System Safety/Security Certifiable Items List (CIL)
Revisions
No. | Date | Description | ORIG | CHKR | Contractor Approval | Agency Approval
0 | 2015-10-15 | Base Line Draft | RS

## CIL Template
FQ16005 | [5 empty] | Installation & Construction Conformance Checklist |  |  | Testing & Inspection Conformance Checklist |  |  | Final Verification |  |  | Certifiable Items List Template Concurrence:
Level 1 - Element | Level 2 - Sub-Element | Level 3 - Item | Level 4 - Sub (1) | level 5 - Sub (2) Item | Item Description | Doc Ref | Verified By | Date | Doc Ref | Verified By | Date | Doc Ref | Verified By | Date | Comments
Facilities
Facilities - General
Provide a copy of the Fairfax County Certificate of occupancy for the appropriate phase of the garage.
Provide a copy of the final certification letter prepared by the Special Inspections Engineer of record and submitted to Fairfax County documenting successful testing and inspection of soil placement & compaction
Facilities - Construction
EXTERNALLY BONDED CFRP CONCRETE STRENGTHENING
Quality Control procedures performed by the Manufacturer shall include, but not be limited to the following
The Manufacturer shall be able to supply testing data to demonstrate system properties and durability of the actual FRP Reinforcement to be used.
Quality Control procedures performed by the Contractor shall include, but not be limited to the following:
The Contractor shall inspect all materials prior to application to assure that they meet specifications and have arrived to the job-site undamaged.
The FRP Reinforcement shall be completely inspected by the contractor during and immediately following application of the composite materials. Conformance with the design drawings, proper alignment of fibers and quality workmanship shall be assured. Entrapped air shall be released or rolled out before the epoxy sets. Defects shall be noted in the Daily Construction Log.
After FRP Reinforcement has cured, the contractor shall inspect the all work to check for voids and or debonding. Repairs shall be made as per Par. 3.07 Repair of Defects, and noted in the Daily Construction Log.
Submit for record test results of the Pull-off test to determine FRP adhesion to concrete substrate
Submit for record Daily Construction Logs kept by the Contractor. These logs shall include the following information:Weather and temperature at application times; Amount of product used and square footage/linear footage of substrate covered; Batch numbers of all products used; Names of all crew members; Any bond-strength tests, noting location, quantity and who performed these tests.
Submit for record compliance with the job site conditions as stated in 03013 1.04
CONCRETE REINFORCEMENT
Manufacturer's certificates.
Mill tests on each heat showing chemical and physical analyses performed in accordance with ASTM A615, as modified by ACI 318.
Record of mill tests traceable to individual reinforcement bars supplied to the project.
CAST-IN-PLACE STRUCTURAL CONCRETE
Furnish the services of an independent testing laboratory. Employment of an independent laboratory does not relieve the Contractor of the obligation to perform the work in accordance with requirements of the Specifications and Drawings. Submit certified results of the tests performed.
Furnish proof that the laboratory satisfies the requirements of the American Council of Independent Laboratories’ Recommended Requirements for Independent Laboratory Qualification. Laboratory need not be a member of the American Council of Independent Laboratories.
Certify that testing equipment has been calibrated by an accredited calibration agency at not more than 12-month intervals using devices of accuracy traceable to the National Institute of Standards and Technology (NIST) or accepted values of material physical constants
Perform strength tests by making not less than one set of standard cylindrical test specimens for each 100 cubic yards of concrete or any portion thereof for each structure. For each work shift, when concrete is delivered, make at least one set of specimens. A set of test specimens consists of at least three standard cylinders from a batch.
Perform slump tests, unit weight and air content tests with no less frequency than that of strength-specimen sets.
a. Determine strengths from standard test specimens according to ASTM C31 and ASTM C172 and cured and tested in accordance with ASTM C39 by the testing laboratory. Core drilling and testing in accordance with ASTM C42.Consider the effects of corrosion-inhibiting admixture and other admixtures on the strength of the concrete, in the concrete mix design. The corrosion-inhibiting admixture and other admixtures must be present in the concrete used for the test of the proposed mix strength. b. Compute and evaluate in accordance with ASTM C94.
1. Take representative samples of concrete mortar. 2. Maximum allowable unit-weight variation of air-free mortar taken from consecutive batches as discharged from mixer: a. Average of two mortar weights: 0.8-percent maximum. b. Average of six mortar weights: 0.5-percent maximum. 3. Maximum allowable weight variation of coarse aggregate per cubic foot of concrete taken from consecutive batches as discharged from mixer. a. Average of two weights: Five-percent maximum.
Batch tickets. Before unloading at the site, submit certification or delivery ticket from concrete supplier with each batch delivered to the site bearing the data as specified in 03300.
PRECAST GLASS FIBER REINFORCED POLYMER CONCRETE PANELS
Erector Responsibility: Prior to installing units, check job site dimensions affecting erection of precast polymer concrete units. Bring to precast polymer manufacturers’ attention any discrepancy between design dimensions and field dimensions that could adversely affect installation. If discrepancies do exist, do not proceed until corrected or until installation requirements are modified as acceptable to Architect.
STRUCTURAL STEEL
Welds
Fillet welds connecting web plates to flange plates: 25 percent of welds inspected by magnetic particle inspection.
For all other fillet-weld connections: 10 percent of welds inspected by magnetic particle inspection.
The Engineer may designate additional items to be inspected by radiography.
Mill testing
For identified stock materials provide three specimens from each heat number, one for tension test, one for bend test and one for Charpy V-notch impact test.
Cut, machine and test specimens in accordance with ASTM A370.
Perform Charpy V-notch impact test for tension flanges and other tension components of aerial structures in accordance with Table 05120-1.
Bolts
The Engineer will randomly select at least five bolts for test purposes from each bin of bolts furnished.
Manufacturer's certification that bolts meet approved testing.
Calibration of wrenches
Employ welding personnel whose qualification is certified in accordance with AWS D1.1. Such certification is to remain in force for the duration of the welding operations under this Contract.
Certification of nondestructive-testing personnel
Perform pertinent testing specified for source quality control. Refer to TABLE 05120-1
CONTROLLED JACKING/SYNCRONOUS LIFT
Ensure hydraulic couplers and fittings are free of dirt before assembly. A quality thread sealant such as Teflon paste or an anaerobic hydraulic sealer should be used to seal the threads on all hydraulic fittings. Contaminants in the hydraulic system will cause poor system performance and/or system failure.
CYLINDER CONTROL CHECK - Before the cylinders are placed under the load, each cylinder should be activated individually and control verified
Verify that the hook-up of the SENSORS, valve wiring, and hydraulic plumbing is correct (i.e. Valve wiring, sensor inputs and hydraulic circuits are matched correctly.)
SPRAYED FIREPROOFING
Samples
Sprayed fireproofing sample 12 inches square by 3/8 inch thick.
Metal lath, anchorage devices, and accessories.
In-place samples of each type of fireproofing sprayed on structural-steel elements where directed and in thickness required for specified hourly fire-resistance ratings for testing by the Engineer.
Quality Assurance Submittals
Qualification Data: For firms and persons specified in the Quality Assurance article to demonstrate their capabilities and experience.
Code Approval: Submit research or evaluation reports of the model code organization acceptable to authorities having jurisdiction showing that sprayed fireproofing products comply with the building code.
Manufacturer’s certification that the sprayed fireproofing system and each product used are compatible with adhesives, primers and other surface coatings on substrates indicated.
Manufacturer Qualifications: Obtain sprayed-on fireproofing system materials from a single manufacturer who evaluates and licenses installers to ensure products are properly installed.
Installer Qualifications: Employ an experienced installer licensed by the sprayed fireproofing manufacturer as having the necessary skill, training, experience and staff to install manufacturer's products as specified and in accordance with manufacturer’s recommendations.
Certify that each product in the sprayed fireproofing system is compatible with adhesives, primers, and other surface coatings on substrates.
Tile
Installer Qualifications: Engage an experienced installer who has completed tile installations similar in material, design, and extent to that indicated for this Project and with a record of successful in-service performance.
ANSI Tile Installation Standards: Comply with parts of ANSI A108 series of tile installation standards in "Specifications for Installation of Ceramic Tile" that apply to types of setting and grouting materials and to methods indicated in ceramic tile installation schedules.
TCA Installation Guidelines: TCA's "Handbook for Ceramic Tile Installation." Comply with TCA installation methods indicated in ceramic tile installation schedules.
SNAP IN METAL PAN CEILINGS
Structural Performance: Exterior grade snap-in metal pan ceilings shall withstand exterior exposure and the effects of gravity loads and the following loads and stresses without showing permanent deformation of ceiling system components including pans and suspension system; noise or metal fatigue caused by vibration, deflection, and displacement of ceiling units; or permanent damage to fasteners and anchors.
Wind Load: Uniform pressure 40 lbf/sq. ft. acting inward or outward.
Thermal Movements: Allow for thermal movements from ambient and surface temperature changes. Base calculations on surface temperatures of materials. a. Temperature Change (Range): 100 deg F (55 deg C).
FIELD QUALITY CONTROL INCLUDING POWER-ACTUATED FASTENERS AND POSTINSTALLED ANCHORS
Provide record of compliance with all sections and parts of 09513 3.04 FIELD QUALITY CONTROL INCLUDING POWER-ACTUATED FASTENERS AND POSTINSTALLED ANCHORS:
AIR CONDITIONING PYLONS
Pressure Test: 1. Include pylon in ductwork pressure test as specified in Section 15810
Balancing and Testing: 1. Include balancing of pylons in balancing and testing of system specified in Section 15950.
DUCTWORK
Air-Leak Tests for Accessible Ductwork: Perform air-leak tests in accordance with SMACNA HVAC Air Duct Leakage Test Manual.
Air-Leak Test for Embedded Ductwork: Test ductwork with internal air pressure of six inches wg. in accordance with SMACNA.
SYSTEM BALANCING AND TESTING
After completion of installation of heating, exhaust and air-conditioning systems, and prior to acceptance by the Engineer, adjust and balance air-handling systems, and appurtenances applicable to those systems to deliver the air quantities as specified and as shown. Make final tests after modifications are completed. Seal instrument test holes upon completion of balancing operation.
Air Balance: 1. Perform testing in accordance with referenced NEBB Standard, ASHRAE 111 or other approved standard. 2. Perform tests, adjust and balance when outside conditions approximate design conditions as shown for heating and cooling functions.
Comments
[14 empty] | Verified By |  |  | Date | MC Special Inspection Sign Off
[14 empty] | MO. CO. |  | WMATA SAFE
Compressive Strength Test Results, slump, air content and concrete temperature.
To include documentation from engineer of record for acceptance of failed CSL tests.
As Builts performed by surveyor licensed in the state of Maryland.
Engineer of record acceptance of Balter reports for competent rock.
Plain and Epoxy Coated
Plain and Epoxy Coated
Compressive Strength Test Results, slump, air content and concrete temperature.
Replaced Secant Pile Wall

## Initials Legend
Design |  |  |  |  | Construction / Installation |  |  |  |  | Startup / Testing
Initial | Discipline | First Name | Last Name | Company/Office | Initial | Discipline | First Name | Last Name | Company/Office | Initial | Discipline | First Name | Last Name | Company/Office
CIL Configuration Management
Initial | Discipline | First Name | Last Name | Company/Office

## ABB
Abbreviations: |  | Discipline Codes
ADAAG | American Disabilities | A - Architectural
AHJ | Authority Having Jurisdiction | B - Bridges and Aerial
AORA | Area Of Rescue Assistance | C - Civil (Grading, Drainage and ROW)
ASCE | American Society of Civil Engineers | E - Electrical
ATC | Automatic Train Control | F - Communications
CCTV | Closed Circuit Television | G - Geotechnical
COMM | Communication | J - Train Control
DGS | Department of General Services | M - Mechanical
DSCP | Design Standard Change Proposal | P - Traction Power
ETEC | Emergency Transportation and Evacuation Cart | R - Track and Alignment
fc | Foot-candles | S - Structural
FIA | Fire & Intrusion Alarm system | T - Civil (Traffic and Roadway)
FLS | Fire Life Safety | U - Civil (Utilities)
HVAC | Heating, Ventilation, and Air Conditioning | Z - Engineering Management
IAW | In Accordance With | SS - System Safety
IBC | International Building Code
IDS | Intrusion Detection System
IDW | Intrusion Detection Warning
LAN | Local Area Network
NEC | National Electrical Code
NFPA | National Fire Protection Association
OCC | Operation Control Center
OSHA | Occupation Safety Health Association
PA | Public Address
PIDS | Passenger Information Display System
SCADA | Supervisory Control and Data Acquisition
SCWG | Safety/Security Certification Working Group
SIER | Special Inspections Engineer of Record
SPEC | Specification
TBD | To Be Determined
UPS | Uninterruptable Power Supply
WAN | Wide Area Network
WMATA | Washington Metropolitan Area Transportation Authority